## 2020
RANK | DIV/DEP | In-Charge | SOURCE | MAIN PROJECT | PROJECT NAME | STATUS | EST DAYS |  | QTR | EST DAYS | START | TARGET | REMARKS
1 |  |  |  | INTEGSYS | Digital G-Card (QR Code) | AI | [5 empty] | Set After Mtg GCard | MIS GMO / Issue Temp Laptop
1 |  | Mac, Jovan |  | TelecomFX | POS Mobile | for Demo | 24 | JAVA |  | 12 |  | 2020-01-11 | January 2nd week
1 |  | Mac, Jovan |  | IntegSysFX | POS Spareparts | for Demo | 6 | JAVA |  | 3 |  | 2019-11-30 | January 2nd week
1 |  | Marlon, Michael |  |  | API Partner Integration | On-going |  | PHP/JAVA |  | ? |  |  | For Testing
1 | MP | Marlon, Michael |  |  | Oguard |  |  |  |  | ? |  | 2019-12-01 | for oppo (MP Loan)
1 | CSS | Marlon, Mac, Michael, Jeff, Jovan |  |  | CI Speed Credit Scoring | BI |  | PHP/JAVA/ANDROID/.NET |  | 30 |  | 2019-12-30 | Impementation Jan 2020
1 |  | Jef, Jovan |  | RIMS | Edocuments (CR Only) | Working |  | JAVA |  | ? |  |  | For Presentation November 19, 2019 (Phase 1 - CR Only)
1 | CSS | Jef, Jovan |  | LRTrckr | Collection Efficiency Monitoring thru DCP | On-going | 6 | VB6 |  | 12
2 |  |  |  | spWIMS | Barcode Reader / ASM |  | 6 | VB6 |  | 6
2 |  |  |  | Telecom | MP Trade In | On-going | 7 | VB6 |  | 14 |  | 2019-12-07 | Billing, Payment Posting & Transfer
3 |  |  |  | GENACCTG | MP Consignment Payment |  |  | VB6
4 | 2H |  |  | mcWIMS | Update Price to the nearest 50 (2H Pricing) |  | 2 | VB6 |  | 2 |  |  | Strict Implement
4 | ASM |  |  | spWIMS | Allocate Inventory for SP Customer Order |  | 6 | VB6 |  | 10
4 | ASM |  |  | spWIMS | Add Branch Inquiry searching in Customer order |  | 3 | VB6 |  | 4 |  |  | All E Items
5 | FINANCE |  |  | IntegSys | Recurring Expenses |  | 6 | VB6 |  | 8 |  |  | With allert & notification (for study existing)
6 | FINANCE |  |  | IntegSys | Cash Advance | for Testing | 3 | VB6 |  | 6 |  |  | Branches/ Entry Cash Advance Transaction (Request)
7 | MIS |  |  | Telecom | MP Inventory Count |  | 6 | VB6 |  | 12
[5 empty] | Android (IntegSys) | Deferred
[5 empty] | Branch Authentication Thru Biometrics | Deferred
[5 empty] | Text Reminders for Employees | Deferred
[5 empty] | Service by Appointment (Study) | Deferred
|  |  |  | INTEGSYS | DTR Posting | ongoing FI
|  |  |  | INTEGSYS | Activity Inquiry (Laptop) | Existing | 1 | VB6 |  | 2 |  |  | Issue Laptop
8 |  |  | P | SMS | Approval Code (S’Jo, S’ Guan, S’ Arnold) |  |  | .NET/JAVA |  | 6 |  |  | Thru Text
|  |  |  | GENACCTG | Payment Text Request | FI |  | VB6 |  |  |  |  | For Presentation November 19, 2019
[5 empty] | Text Blast Report | For Development | 1 | VB6 |  | 6
8 |  | Mike | P |  | Android (Cash Count) | for Testing |  | ANDROID |  |  |  |  | For Presentation November 19, 2019
|  |  |  | INTEGSYS | System based Trade-In |  |  | VB6 |  | 7
|  |  |  | LRTrckr | Guanzon Car Trade Credit Application |  |  | .NET |  | 7
|  |  |  | INTEGSYS | Hot Item Model | FI |  | VB6
| TELE |  |  |  | ORCR Notification | Hold
|  |  |  | INTEGSYS | MC Transfer Approval | for FI |  | VB6
|  |  |  | Telecom | MP Purchasing via Email |  | 2 | VB6 |  | 2
| TELE |  |  |  | Referral Incentive (Gcard Points) (Customer) | [7 empty] | For Study
| TELE |  |  |  | Recording (BPO) |  | 1 |  |  | ? |  |  | Globe (Meeting on Wednesday)
8 | TELE |  | P |  | Notification for Collecting & Selling Branch |  | 1 | VB6/JAVA |  | 3 |  |  | Selling Branch will release the cash
8 | TELE |  | P |  | Text Blast (Masking) 0.30/sms |  | 3 | JAVA |  | 6 |  |  | For unanswered cash loan (API)
| ASM |  |  | spWIMS | SOA Unpaid PO Receiving(Reports) | DI | 1 | VB6/CRYSTAL |  | 4
| ASM |  |  | spWIMS | Warranty Claims(Reports) |  |  | VB6/CRYSTAL |  | 4
| ASM |  |  | spWIMS | FSC & WRC (Reports) |  |  | VB6/CRYSTAL |  | 4
| ASM |  |  | spWIMS | Supplier Service Report(Reports) | DI |  | VB6/CRYSTAL |  | 4 |  |  | With dealer Report form
| FINANCE |  |  | IntegSys | Petty Cash | Implemention |  | VB6 |  |  |  |  | Branches
8 | FINANCE |  | P | IntegSys | Integrate Purchase Order MC / MP thru Gen Acctg |  | 3 | VB6 |  | 8
| FINANCE |  |  | GENACCTG | Payroll Reports |  | 2 | VB6/CRYSTAL |  | 16 |  |  | New Employee, Adjustment, Loans, Aging of unpaid claims
| FINANCE |  |  | GENACCTG | Advance Payment Monitoring/COD |  | 3 | VB6 |  | 6 |  |  | Items already received (eg. LAZADA, Amazon)
| SALES |  |  | IntegSys | MC Aging | DI |  | VB6 |  | 2 |  |  | Branches/ Update printing
| MIS |  |  |  | Asset System (Sales & Maintenance) | Deferred
| SALES |  |  | IntegSys | Rebate Escalation |  | 1 | VB6 |  | 2 |  |  | 200, 300, 400 Rebate
| SALES |  |  | IntegSys | Encoding of PO Number (MC PO Receiving) |  | 1 | VB6 |  | 2
| MIS |  |  | IntegSys | CR Inventory for Cash loan |  | 3 | .NET |  | 6
| MIS |  |  | IntegSys | Log-In to other branch w/ cash count & random sp inv |  | 6 | VB6 |  | 14
| MIS |  |  |  | Force Inventory Check | Deferred | [6 empty] | Branch
8 | MIS | Mike, Xavier | P | Website | WEBSITE (event schedules) |  | 1 | PHP/JAVA/WORDPRESS |  | 10 |  |  | PHP -> Perpetual
8 | MIS | Mike | P |  | Gapp (event schedules, service reminder) |  | 6 | PHP/JAVA/ANDROID |  | 45
8 | MIS | Mike | P | Android | AH Branch Performance Monitoring |  |  | PHP/ANDROID |  | 45
8 | CSS | She | P |  | Collection Monitoring(monitored by Branch) |  | 3 | VB6/CRYSTAL |  | 5
| CSS |  |  | IntegSys | AR Ledger Printing | for AI |  | VB6 |  | 2 |  |  | Branches
| RDS |  |  | RIMS | Branch Inventory Posting (CR) |  | 1 |  |  | 2
| RDS |  |  | RIMS | Change Unit, Name, Address Monitoring(Reports) |  | 1 | VB6/CRYSTAL |  | 3
| HCM |  |  |  | Vacancy Posting Thru FB / Application thru Website |  | 1 | PHP/JAVA/WORDPRESS |  | 6 |  |  | PHP -> Perpetual
8 | HCM | Sir Marlon | P |  | Random Sending of Payslip (To be checked Selected Employee) |  | 1 | JAVA/JASPER |  | 15
| HCM |  |  |  | IOM Issuance |  | 1 | VB6/JAVA/JASPER |  | 15 |  |  | memo
[7 empty] | 119 |  |  | 378
***PROJECT FROM SIR REX
1 |  | Sir Marlon |  |  | Adjust term loan for AR Customers(2Months)
5 |  | Mac |  |  | Approval code for attendance entry to android phones |  |  |  |  | 2
|  | Sir Marlon |  |  | Reports thru web (API)
***NEW SCHEDULING
|  | Implementor |  |  | Server-Client Replication for branches
2 |  | Sir Jeff, Xavier |  |  | E-Commerce |  |  | VB6 |  | 2
Utility, Extract, Report
4 |  | Sir Jeff, Jovan |  |  | E-Documents |  |  | JAVA
|  | Sir Marlon |  |  | Payroll Encryptiion System
3 |  | SEG |  |  | CI Speed Scoring |  |  | PHP/JAVA/ANDROID/.NET
6 |  | Mac |  |  | GCARD - non chip card |  |  | JAVA/PHP |  | 5
Note on G9: ====== ID#AAAAJNZezZ4 Marlon Sayson (2020-03-17 03:25:46) 2020.03.17 11:24 am Already in use by Madam Lo according to She but still needs to add a feature to include Telemarketing.
Note on G23: ====== ID#AAAAGS4R9TE Marlon Sayson (2020-03-13 07:00:09) 2020.03.13 02:59pm As of date already implemented in 5 Areas
Note on G26: ====== ID#AAAAJNZezZk Marlon Sayson (2020-03-17 03:18:41) 2020.03.17 11:18am Fully implement according to Madam She
Note on G31: ====== ID#AAAAGSeCDEQ Marlon Sayson (2020-03-13 03:28:40) 2020.03.13 11:28am According to she naimplement na ito
Note on G33: ====== ID#AAAAGSeCDEM Marlon Sayson (2020-03-13 03:27:58) 2020.03.13 11:25 am Creation of IOC assigned to She.
Note on G39: ====== ID#AAAAGSxA7uw Marlon Sayson (2020-03-13 08:24:44) 2020.03.13 04:23pm implemented according to she after talking to she.
Note on G42: ====== ID#AAAAGSxA7u0 Marlon Sayson (2020-03-13 08:24:53) 2020.03.13 04:23pm implemented according to she after talking to she.
Note on G47: ====== ID#AAAAJNZezZw Marlon Sayson (2020-03-17 03:20:33) 2020.03.17 11:20am Already used by Madam Rowie according to She
Note on G58: ====== ID#AAAAGSrFfiM Marlon Sayson (2020-03-13 05:08:10) 2020.03.13 01:07pm Instructed she to implement it Areawide. Waiting for IOC/manual to be created.

## Sheet2
RANK | DIV/DEP | In-Charge | SOURCE | MAIN PROJECT | PROJECT NAME | STATUS | EST DAYS |  | QTR | EST DAYS | WFH EST DAY | TESTING EST | START | TARGET | REMARKS
1 |  |  |  | INTEGSYS | Digital G-Card (QR Code) | AI | [7 empty] | Set After Mtg GCard | MIS GMO / Issue Temp Laptop
1 |  | Mac, Jovan |  | TelecomFX | POS Mobile | for Demo | 24 | JAVA |  | 12 |  |  |  | 2020-01-11 | January 2nd week
1 |  | Mac, Jovan |  | IntegSysFX | POS Spareparts | for Demo | 6 | JAVA |  | 3 |  |  |  | 2019-11-30 | January 2nd week
1 |  | Marlon, Michael |  |  | API Partner Integration | On-going |  | PHP/JAVA |  | ? |  |  |  |  | For Testing
1 | MP | Marlon, Michael |  |  | Oguard |  |  |  |  | ? |  |  |  | 2019-12-01 | for oppo (MP Loan)
1 | CSS | Marlon, Mac, Michael, Jeff, Jovan |  |  | CI Speed Credit Scoring | BI |  | PHP/JAVA/ANDROID/.NET |  | 30 |  |  |  | 2019-12-30 | Impementation Jan 2020
1 |  | Jef, Jovan |  | RIMS | Edocuments (CR Only) | Working |  | JAVA |  | ? |  |  |  |  | For Presentation November 19, 2019 (Phase 1 - CR Only)
1 | CSS | Jef, Jovan |  | LRTrckr | Collection Efficiency Monitoring thru DCP | On-going | 6 | VB6 |  | 12
2 |  |  |  | spWIMS | Barcode Reader / ASM |  | 6 | VB6 |  | 6
2 |  |  |  | Telecom | MP Trade In | On-going | 7 | VB6 |  | 14 |  |  |  | 2019-12-07 | Billing, Payment Posting & Transfer
3 |  |  |  | GENACCTG | MP Consignment Payment |  |  | VB6
4 | 2H |  |  | mcWIMS | Update Price to the nearest 50 (2H Pricing) |  | 2 | VB6 |  | 2 |  |  |  |  | Strict Implement
4 | ASM |  |  | spWIMS | Allocate Inventory for SP Customer Order |  | 6 | VB6 |  | 10
4 | ASM |  |  | spWIMS | Add Branch Inquiry searching in Customer order |  | 3 | VB6 |  | 4 |  |  |  |  | All E Items
5 | FINANCE |  |  | IntegSys | Recurring Expenses |  | 6 | VB6 |  | 8 |  |  |  |  | With allert & notification (for study existing)
6 | FINANCE |  |  | IntegSys | Cash Advance | for Testing | 3 | VB6 |  | 6 |  |  |  |  | Branches/ Entry Cash Advance Transaction (Request)
7 | MIS |  |  | Telecom | MP Inventory Count |  | 6 | VB6 |  | 12
8 | MIS | Xavier | P | Website | WEBSITE (event schedules) |  | 1 | PHP/JAVA/WORDPRESS |  | 10 | continuous | 1 |  |  | PHP -> Perpetual
9 | MIS | Mac, Mike | P |  | Gapp (event schedules, service reminder) |  | 6 | PHP/JAVA/ANDROID |  | 45 | 45 | 1
10 | MIS | Mac, Mike | P | Android | AH Branch Performance Monitoring |  |  | PHP/ANDROID |  | 45 | 45 | 1
11 | CSS | She | P |  | Collection Monitoring(monitored by Branch) |  | 3 | VB6/CRYSTAL |  | 5 | 3 | 1
12 | TELE | Mac, Mike | P |  | Notification for Collecting & Selling Branch |  | 1 | VB6/JAVA |  | 3 | 3 | 1 |  |  | Selling Branch will release the cash
13 |  | Mike | P |  | Android (Cash Count) | for Testing |  | ANDROID |  |  | 1 | 1 |  |  | For Presentation November 19, 2019
14 | TELE | Mac | P |  | Text Blast (Masking) 0.30/sms |  | 3 | JAVA |  | 6 | 3 | 1 |  |  | For unanswered cash loan (API)
15 |  | Sir Jeff | P | SMS | Approval Code (S’Jo, S’ Guan, S’ Arnold) |  |  | .NET/JAVA |  | 6 | 6 | 1 |  |  | Thru Text
16 | FINANCE | SEG | P | IntegSys | Integrate Purchase Order MC / MP thru Gen Acctg |  | 3 | VB6 |  | 8 | 6 | 2
17 | HCM | Sir Marlon | P |  | Random Sending of Payslip (To be checked Selected Employee) |  | 1 | JAVA/JASPER |  | 15
[5 empty] | Android (IntegSys) | Deferred
[5 empty] | Branch Authentication Thru Biometrics | Deferred
[5 empty] | Text Reminders for Employees | Deferred
[5 empty] | Service by Appointment (Study) | Deferred
|  |  |  | INTEGSYS | DTR Posting | ongoing FI
|  |  |  | INTEGSYS | Activity Inquiry (Laptop) | Existing | 1 | VB6 |  | 2 |  |  |  |  | Issue Laptop
|  |  |  | GENACCTG | Payment Text Request | FI |  | VB6 | [6 empty] | For Presentation November 19, 2019
[5 empty] | Text Blast Report | For Development | 1 | VB6 |  | 6
|  |  |  | INTEGSYS | System based Trade-In |  |  | VB6 |  | 7
|  |  |  | LRTrckr | Guanzon Car Trade Credit Application |  |  | .NET |  | 7
|  |  |  | INTEGSYS | Hot Item Model | FI |  | VB6
| TELE |  |  |  | ORCR Notification | Hold
|  |  |  | INTEGSYS | MC Transfer Approval | for FI |  | VB6
|  |  |  | Telecom | MP Purchasing via Email |  | 2 | VB6 |  | 2
| TELE |  |  |  | Referral Incentive (Gcard Points) (Customer) | [9 empty] | For Study
| TELE |  |  |  | Recording (BPO) |  | 1 |  |  | ? |  |  |  |  | Globe (Meeting on Wednesday)
| ASM |  |  | spWIMS | SOA Unpaid PO Receiving(Reports) | DI | 1 | VB6/CRYSTAL |  | 4
| ASM |  |  | spWIMS | Warranty Claims(Reports) |  |  | VB6/CRYSTAL |  | 4
| ASM |  |  | spWIMS | FSC & WRC (Reports) |  |  | VB6/CRYSTAL |  | 4
| ASM |  |  | spWIMS | Supplier Service Report(Reports) | DI |  | VB6/CRYSTAL |  | 4 |  |  |  |  | With dealer Report form
| FINANCE |  |  | IntegSys | Petty Cash | Implemention |  | VB6 | [6 empty] | Branches
| FINANCE |  |  | GENACCTG | Payroll Reports |  | 2 | VB6/CRYSTAL |  | 16 |  |  |  |  | New Employee, Adjustment, Loans, Aging of unpaid claims
| FINANCE |  |  | GENACCTG | Advance Payment Monitoring/COD |  | 3 | VB6 |  | 6 |  |  |  |  | Items already received (eg. LAZADA, Amazon)
| SALES |  |  | IntegSys | MC Aging | DI |  | VB6 |  | 2 |  |  |  |  | Branches/ Update printing
| MIS |  |  |  | Asset System (Sales & Maintenance) | Deferred
| SALES |  |  | IntegSys | Rebate Escalation |  | 1 | VB6 |  | 2 |  |  |  |  | 200, 300, 400 Rebate
| SALES |  |  | IntegSys | Encoding of PO Number (MC PO Receiving) |  | 1 | VB6 |  | 2
| MIS |  |  | IntegSys | CR Inventory for Cash loan |  | 3 | .NET |  | 6
| MIS |  |  | IntegSys | Log-In to other branch w/ cash count & random sp inv |  | 6 | VB6 |  | 14
| MIS |  |  |  | Force Inventory Check | Deferred | [8 empty] | Branch
| CSS |  |  | IntegSys | AR Ledger Printing | for AI |  | VB6 |  | 2 |  |  |  |  | Branches
| RDS |  |  | RIMS | Branch Inventory Posting (CR) |  | 1 |  |  | 2
| RDS |  |  | RIMS | Change Unit, Name, Address Monitoring(Reports) |  | 1 | VB6/CRYSTAL |  | 3
| HCM |  |  |  | Vacancy Posting Thru FB / Application thru Website |  | 1 | PHP/JAVA/WORDPRESS |  | 6 |  |  |  |  | PHP -> Perpetual
| HCM |  |  |  | IOM Issuance |  | 1 | VB6/JAVA/JASPER |  | 15 |  |  |  |  | memo
***PROJECT FROM SIR REX
1 |  | Sir Marlon |  |  | Adjust term loan for AR Customers(2Months) |  |  | VB6/.NET |  |  | - | -
5 |  | Mac |  |  | Approval code for attendance entry to android phones |  |  | ANDROID |  |  | 3 | 1
|  | Sir Marlon |  |  | Reports thru web (API) |  |  | PHP/ANDROID |  |  | - | -
***NEW SCHEDULING
|  | Implementor |  |  | Server-Client Replication for branches |  |  | MYSQL
2 |  | Sir Jeff, Xavier |  |  | E-Commerce |  |  | VB6 |  |  | 3 | 3
Utility, Extract, Report
4 |  | Sir Jeff, Jovan |  |  | E-Documents |  |  | JAVA |  |  | 6 | 6
|  | Sir Marlon |  |  | Payroll Encryption System | [5 empty] | - | -
3 |  | SEG |  |  | CI Speed Scoring |  |  | PHP/JAVA/ANDROID/.NET |  |  | - | -
6 |  | Mac |  |  | GCARD - non chip card |  |  | JAVA/PHP |  |  | 4 | 1
Note on L20: Michael Cuison: Parang overscheduled po.
Note on L21: Michael Cuison: Parang overscheduled po.
Note on E23: Michael Cuison: Android po ba ito?

## Sheet1
Code | Description
IG | Information Gathering
AD | Analysis/Design
DV | Development
TS | Testing
BI | Branch Implementation
DI | Department Implementation
AI | Area Implementation
FI | Full Implementation
DF | Deferred