## 2019
STRAT PLAN REVIEW
2018 PROJECT PLAN
PROJECT | DEPARTMENT | DIVISION | TIMELINE | TARGET | STATUS | REMARKS | COMMENTS | NEW TARGET
Digital G-Card (QR Code) |  | MC | 2019-08-01 |  | Working | Area 9 (Pilot Area) | Sched Visit of MIS
Android (IntegSys) |  | MC | 2019-04-01 |  | Hold | Install in Tablet Windows 10 (SGH) | continue used for hot areas
Payroll Engineering | Monarch |  | 2019-03-01 | 2019-09-01 | Working | Unable to read finger print afterwork | pin code afternoon
Activity Inquiry (Android-Tablet) |  | MC | 2019-03-01 |  | For Development |  |  | 2020-01-01
Branch Authentication Thru Biometrics |  | MC |  |  | Hold | Two or more PC/Branch | Purchase additional Reader per pc
Text Reminders for Employees |  | MC/MP |  |  |  | Not Priority
Approval Code (S’Jo, S’ Guan, S’ Arnold) |  | MP |  |  | Hold | Not Priority | New Proposed SMS Approval
Petty Cash Expenses | FINANCE | MC |  |  | Working | Main Office | Implementaton to Branches
Insurance (TPL/COC) Posting | FINANCE | MC |  |  | Working | Main Office
MP Consignment Payment | FINANCE | MP |  |  | For Development | Create new rules for inventory | Additional Category and create new barcode | 2019-12-01
Payment Text Request | FINANCE | MC |  |  | Implementation | Dagupan Area
E-commerce |  | MP |  |  | Working | We Deliver Program | More Adz
Barcode Reader | ASM | MC |  |  | For Development | Update System | for verification | 2019-12-01
Text Blast Report | ASM | MC |  |  | For Development |  | create utiltiy |  | check response time
Expand Riders Club Program | ASM | MC |  |  | Working | No Updates from Gcard Dep |  |  | mtg for gcard department
Service by Appointment (Study) | ASM | MC |  |  | Hold | Not Priority | Add G-App
2019 PROJECT
CI Approval Code Thru SMS |  | MC | 2019-01-01 |  | Working
Unencoded Transaction Entry |  | MC |  |  | Working
DTR Posting |  | MC |  | 2019-11-01 | For Testing
Outgoing Call for MP Sales | TELEMARKETING | MP | 2019-03-01 |  | Working | Utility for MP Clients
Android (Cash Count) |  | MP/MC |  |  | For Testing
Meal Voucher | Monarch |  |  |  | Working
System based Trade-In |  | ASM | 2019-03-01 |  | For Development
Translation of IntegSys |  |  |  |  | HOLD
Guanzon Car Trade Credit Application | Car Trade |  | 2019-03-01 |  | For Development
POS Mobile |  | MP |  |  | Continuation | BIR Compliance
POS Spareparts |  | MC |  |  | Continuation | BIR Compliance
EDocuments |  | RDS | 2019-05-01 | 2019-11-01 | For Testing | Pilot Testing CR Only
Hot Item Model | SALES | MC |  |  | For Activation
MC Transfer Approval |  | MC |  |  | For Activation
MP Trade In | SALES | MC |  |  | For Testing | Billing
PETMgr Updates |  |  |  |  | Working
Employee Leave Credit
Employee Leave Adjustment
Log Processing
Probi Salary Computation as Regular
Payment of Special Holiday for Absent Rank & File
Processing of Salary per Division Overtime
Payroll Monarch
Night Shift Differenctial
Service Charge Distribution
Compressed Time
Compressed Time
Compensation Off
MP Purchasing via Email
CCTV Monitoring (HIK Connect) |  |  |  |  | Continuation
GPS Installation |  |  |  |  | Continuation
API Partner Integration |  |  |  |  | For Testing
IMPLEMENTED PROJECT 2019
General Purchase | Emgineering |  |  |  | Working
Payroll Honda Cars | Honda |  |  |  | Working
Food Inventory | Pedritos |  |  |  | Working
Dashboard (HCM) | HCM | MP/MC |  |  | Working
WebCam | SALES | MC |  |  | Working
Log-IN to other branch | [5 empty] | create report
Computerized Pricelist for Repo
PROPOSE PROJECT 2019
CONTINUE BACK LOGS | [5 empty] | Refer
TEXT APPROVAL | [5 empty] | c/o Sir jo
Asset (Sales & Maintenance)
SMS Incoming/Outgoing | [5 empty] | convert to JAVA
CR Inventory for Trade-Ins
MP Inventory Count | [5 empty] | SP Like
Log-IN to other branch w/cash count for AH only | [6 empty] | random cycle invetory
Credit Application Android |  | MP/MC
Guanzon Apps
Periodic Scheduling Service Notification
AREA MANAGER | Sales
Collection
Deposit
Cancellation (legit)
Payment

## 2020
RANK | DIV/DEP | In-Charge | SOURCE | MAIN PROJECT | PROJECT NAME | STATUS | EST DAYS |  | EST DAYS | START | TARGET | REMARKS
1 |  |  |  | INTEGSYS | Digital G-Card (QR Code) | Working |  |  |  |  | Set After Mtg GCard | MIS GMO / Issue Temp Laptop
1 |  | Mac, Jovan |  | TelecomFX | POS Mobile | On-going | 24 | JAVA | 12 |  | 2020-01-11 | January 2nd week
[5 empty] | Android (IntegSys) | Deferred
1 |  | Mac, Jovan |  | IntegSysFX | POS Spareparts | On-going | 6 | JAVA | 3 |  | 2019-11-30 | January 2nd week
[5 empty] | Branch Authentication Thru Biometrics | Deferred
[5 empty] | Text Reminders for Employees | Deferred
1 |  | Jef, Jovan |  | RIMS | Edocuments (CR Only) | Working |  | JAVA | ? |  |  | For Presentation November 19, 2019 (Phase 1 - CR Only)
1 |  | Marlon, Michael |  |  | API Partner Integration | On-going |  | PHP/JAVA | ? |  |  | For Testing
1 | MP | Marlon, Michael |  |  | Oguard |  |  |  | ? |  | 2019-12-01 | for oppo (MP Loan)
1 | CSS | Marlon, Mac, Michael, Jeff, Jovan |  |  | CI Speed Credit Scoring |  |  | PHP/JAVA/ANDROID | 30 |  | dec -30-2019 | Impementation Jan 2020
1 | CSS | Jef, Jovan |  | LRTrckr | Collection Efficiency Monitoring thru DCP |  | 6 | VB6 | 12
[5 empty] | Service by Appointment (Study) | Deferred
2 |  |  |  | spWIMS | Barcode Reader / ASM |  | 6 | VB6 | 6
2 |  |  |  | Telecom | MP Trade In | On-going | 7 | VB6 | 14 |  | 2019-12-07 | Billing, Payment Posting & Transfer
3 |  |  |  | GENACCTG | MP Consignment Payment |  |  | VB6
4 | 2H |  |  | mcWIMS | Update Price to the nearest 50 (2H Pricing) |  | 2 | VB6 | 2 |  |  | Strict Implement
4 | ASM |  |  | spWIMS | Allocate Inventory for SP Customer Order |  | 6 | VB6 | 10
4 | ASM |  |  | spWIMS | Add Branch Inquiry searching in Customer order |  | 3 | VB6 | 4 |  |  | All E Items
5 | FINANCE |  |  | IntegSys | Recurring Expenses |  | 6 | VB6 | 8 |  |  | With allert & notification (for study existing)
6 | FINANCE |  |  | IntegSys | Cash Advance |  | 3 | VB6 | 6 |  |  | Branches/ Entry Cash Advance Transaction (Request)
7 | MIS |  |  | Telecom | MP Inventory Count |  | 6 | VB6 | 12
|  |  |  | INTEGSYS | DTR Posting | Implementation
|  |  |  | INTEGSYS | Activity Inquiry (Laptop) | Existing | 1 | VB6 | 2 |  |  | Issue Laptop
|  |  |  | SMS | Approval Code (S’Jo, S’ Guan, S’ Arnold) |  |  | .NET/JAVA | 6 |  |  | Thru Text
|  |  |  | GENACCTG | Payment Text Request | Implementation |  | VB6 |  |  |  | For Presentation November 19, 2019
[5 empty] | Text Blast Report | For Development | 1 | VB6 | 6
[5 empty] | Android (Cash Count) | Implementation |  | ANDROID |  |  |  | For Presentation November 19, 2019
|  |  |  | INTEGSYS | System based Trade-In |  |  | VB6 | 7
|  |  |  | LRTrckr | Guanzon Car Trade Credit Application |  |  | .NET | 7
|  |  |  | INTEGSYS | Hot Item Model | Implemention |  | VB6
| TELE |  |  |  | ORCR Notification | Hold
|  |  |  | INTEGSYS | MC Transfer Approval | Implemention |  | VB6
|  |  |  | Telecom | MP Purchasing via Email |  | 2 | VB6 | 2
| TELE |  |  |  | Referral Incentive (Gcard Points) (Customer) | [6 empty] | For Study
| TELE |  |  |  | Recording (BPO) |  | 1 |  | ? |  |  | Globe (Meeting on Wednesday)
| TELE |  |  |  | Notification for Collecting & Selling |  | 1 | VB6/JAVA | 3 |  |  | Selling Branch will release the cash
| TELE |  |  |  | Text Blast (Masking) 0.30/sms |  | 3 | JAVA | 6 |  |  | For unanswered cash loan (API)
| ASM |  |  | spWIMS | SOA Unpaid PO Receiving | Reports | 1 | VB6/CRYSTAL | 4
| ASM |  |  | spWIMS | Warranty Claims | Reports |  | VB6/CRYSTAL | 4
| ASM |  |  | spWIMS | FSC & WRC | Reports |  | VB6/CRYSTAL | 4
| ASM |  |  | spWIMS | Supplier Service Report | Reports |  | VB6/CRYSTAL | 4 |  |  | With dealer Report form
| FINANCE |  |  | IntegSys | Petty Cash | Implemention |  | VB6 |  |  |  | Branches
| FINANCE |  |  | IntegSys | Integrate Purchase Order MC / MP thru Gen Acctg |  | 3 | VB6 | 8
| FINANCE |  |  | GENACCTG | Payroll Reports |  | 2 | VB6/CRYSTAL | 16 |  |  | New Employee, Adjustment, Loans, Aging of unpaid claims
| FINANCE |  |  | GENACCTG | Advanve Payment Monitoring/COD |  | 3 | VB6 | 6 |  |  | Items already received (eg. LAZADA, Amazon)
| MIS |  |  |  | Asset System (Sales & Maintenance) | Deferred
| SALES |  |  | IntegSys | MC Aging | Implemention |  | VB6 | 2 |  |  | Branches/ Update printing
| SALES |  |  | IntegSys | Rebate Scallation |  | 1 | VB6 | 2 |  |  | 200, 300, 400 Rebate
| SALES |  |  | IntegSys | Encoding of PO Number (MC PO Receiving) |  | 1 | VB6 | 2
| MIS |  |  | IntegSys | CR Inventory for Cash loan |  | 3 | .NET | 6
| MIS |  |  | IntegSys | Log-In to other branch w/ cash count & random sp inv |  | 6 | VB6 | 14
| MIS |  |  |  | Force Inventory Check | Deferred | [5 empty] | Branch
| MIS |  |  | Website | WEBSITE (event schedules) |  | 1 | PHP/JAVA/WORDPRESS | 10 |  |  | PHP -> Perpetual
| MIS |  |  |  | Gapp (event schedules, service reminder) |  | 6 | PHP/JAVA/ANDROID | 45
| MIS |  |  |  | AH Branch Performance Monitoring |  |  | PHP/ANDROID | 45
| CSS |  |  |  | Collection Monitoring(monitored by Branch) |  | 3 | VB6/CRYSTAL | 5
| CSS |  |  | IntegSys | AR Ledger Printing | Implement |  | VB6 | 2 |  |  | Branches
| RDS |  |  | RIMS | Branch Inventory Posting (CR) |  | 1 |  | 2
| RDS |  |  | RIMS | Change Unit, Name, Address Monitoring | Reports | 1 | VB6/CRYSTAL | 3
| HCM |  |  |  | Vacancy Posting Thru FB / Application thru Website |  | 1 | PHP/JAVA/WORDPRESS | 6 |  |  | PHP -> Perpetual
| HCM |  |  |  | Random Sending of Payslip (To be checked Selected Employee) |  | 1 | JAVA/JASPER | 15
| HCM |  |  |  | IOM Issuance |  | 1 | VB6/JAVA/JASPER | 15 |  |  | memo
[7 empty] | 119 |  | 378