## Sheet1
Date | Project Code | Particular | Est. Days | Start | Finish | Remarks
2020-10-19 | Lender | Partner Payment Integration | 0 | 2020-10-19 | 2020-10-19 | Adjust date to actual date of payment from payment center
2020-10-19 | Lender | Partner Payment Integration | 0 | 2020-10-19 | 2020-10-19 | Add "Penalty" field on OR Release
2020-10-19 | LRTrackr | Collection Unit |  | 2020-10-21 | 2020-10-21 | Explain scheduling to M' Loraine / get suggestions
2020-10-19 | FBPromo | Transaction Information Entry | 1 | 2020-10-19 | 2020-10-21 | Sending of link to customer upon entry
2020-10-19 | FBPromo | Web pages | 1 | 2020-10-19 | 2020-10-23 | Webpage validation adjustment
2020-10-19 | LRTrackr | Account Status Update | 0 |  |  | Check recalculate utilities from vb6 to vb.net on where the update happens
2020-10-19 | Utility | Partner Payment Integration | 0 |  |  | Transfer to linux server cron
2020-10-19 | Utility | AR Accounts Mobile Activator | 0 |  |  | Transfer to linux server cron
2020-10-19 | Utility | Create/Modify Leads of TLM | 0 |  |  | Transfer to linux server cron
2020-10-20 | IntegSys | Credit Application |  | 2020-10-20 | 2020-10-20 | Multiple Step Error (Update append field size for address)
2020-10-20 | FB Promo | API |  | 2020-10-20 | 2020-10-20 | Get transaction promo basis
2020-10-21 | Alacart | Servo POS System |  | 2020-10-21 | 2020-10-21 | Check system updates on all POS stations
2020-10-21 | Website | Backup files and database |  | 2020-10-21 | 2020-10-21
2020-10-22 | LRTrackr | Lender->OR Release |  | 2020-10-22 | 2020-10-22 | Check can't be OR Released account (Account already released and deleted, status on XAPITrans was not rollback then)
2020-10-23 | GCard System | Unable to save online points entry |  | 2020-10-23 | 2020-10-23 | LRPayment cGCrdPstd is already 1 or something happen on the connection that's why it does not continue
2020-10-23 | FBPromo | Transaction Information Entry |  | 2020-10-23 | 2020-10-23 | Initial testing, sent a copy to implementation team
2020-10-24 | FBPromo | Facebook Problem upon clicking like button |  | 2020-10-24 |  | This error just occurred on 2020-10-23 previous days are okay
2020-10-24 | Lender | Check if error catching exists when saving monthly payment |  | 2020-10-24 | 2020-10-24 | Catch claus is present, will check if the branch dll was updated
2020-10-24 | IntegSys | Credit Application type mismatch when saving GOCAS |  | 2020-10-24 | 2020-10-24 | Invalid birthday
2020-10-24 | PETMgr | Check GCO Timkeeper not appearing option for log position | 0 | 2020-10-26 | 2020-10-26 | Recompiled for GK mirror for GCO with different user credential to avoid duplicate entry
2020-10-26 | Server | Unable to start mysql server | 0 | 2020-10-26 | 2020-10-26 | Unmounted hardrive, just remounted the drive
2020-10-26 | spWIMS | Purchasing -> SP PO Receiving -> ggcSPPurchasing |  | 2020-10-26 | 2020-10-28 | Adjust to POS like approach when loading detail
2020-10-26 | Food POS | Capture servo item list to guanzon POS |  | 2020-10-26 | 2020-10-26
2020-10-27 | Dashboard | Compilation of program |  | 2020-10-27 | 2020-10-27 | Transferred to implementation group
2020-10-28 | Server | Unable to start mysql server | 0 | 2020-10-28 | 2020-10-28 | Unmounted hardrive, just remounted the drive
2020-10-28 | GCard System | Fix date time value on QR Code accounts |  | 2020-10-28 | 2020-10-28 | Recompiled transferred to implementation group
2020-10-28 | GCard System | Trace problem of voiding online entry |  | 2020-10-28 | 2020-10-28 | Double entry of reference number on LR Payment so the system detects different account
2020-10-28 | spWIMS | Sales -> Wholesale |  | 2020-11-03 | 2020-11-04
2020-10-28 | spWIMS | Sales -> Sales Return |  |  |  | deffered(not frequently used or few items)
2020-10-28 | spWIMS | Wholesale -> Issuance |  |  |  | deffered(quantity to issue is based on the approved quantity)
2020-10-28 | spWIMS | Purchasing -> SP PO Return |  |  |  | deffered(not frequently used or few items)
2020-10-31 | FBPromo | Utility to create ramdom raffle numbers | 0 | 2020-10-31 | 2020-10-31 | Pre generated random numbers on FB_Raffle_Ticket
2020-10-31 | FBPromo | Adjust API to retreive random raffle no pre generated | 0 | 2020-10-31 | 2020-10-31
2020-11-02 | Guanzon App | Trace duplicate key on adding existing but deactivated gcard on account | 0 | 2020-11-02 | 2020-11-02 | Add validation on updating old gcard records of the user
2020-11-02 | IntegSys | Trace unknown field detected on mc transfer posting | 0 | 2020-11-02 | 2020-11-02 | Need update for IntegSys.exe, ggcWarehouse.dll
2020-11-02 | Food POS | Asked servo if they a system that supports POS networking | 0 | 2020-11-02 | 2020-11-02 | Via support ticket(Morris)
2020-11-02 | Lender | OR Release -> add validation | 0 |  |  | Require reference number on remarks field, must start with BP or CC
2020-11-02 | Lender | ggcAppDriver -> add validation | 0 |  |  | Inactive employees must not able to login ther account anymore
2020-11-02 | Dashboard | Check UI distortion
2020-11-03 | Task | Capture Suzuki sparepart list from Mam Joan Sape | 0 | 2020-11-03 | 2020-11-03
2020-11-04 | PetMgr | Trace why timekeeper not appearing option to place log | 0 | 2020-11-04 | 2020-11-04 | Max hours is 23, greater than this will auto assign the log to current day
2020-11-04 | Task | Run JO Utility M066 San Fernando Multi 172.16.4.182
2020-11-04 | IntegSys | Transaction -> SP Wholesale |  | 2020-11-04 | 2020-11-04
2020-11-04 | Task | Run JO Utility M008 172.16.3.214
2020-11-04 | Lender | Check In-house financing compilation reported by princess
2020-11-05 | LRTrackr | Check route area "out of stack space" error | 1 | 2020-11-05 | 2020-11-06 | Found out wrong procedure of updating barangay cHasRoute and insert on Route_Area_Barangay table
2020-11-05 | FBPromo | Adjust class, add fields to encoding app and add support for a utility call | 1 | 2020-11-05 | 2020-11-06
2020-11-06 | FBPromo | Add fields to API and database to support raffle draw filtering | 0 | 2020-11-06 | 2020-11-06
2020-11-07 | Task | System_Code_Mobile | 0 | 2020-11-07 | 2020-11-07 | Changed mobile number of existing record of CI M05611000473-09478850157 -> 09616288260
2020-11-07 | Lender | MC Payment Posting | 0 | 2020-11-07 | 2020-11-07 | Review unable to encode payments to online points entry
2020-11-07 | GCard System | Online Points | 0 | 2020-11-07 | 2020-11-07 | Review validation for already encoded entry
2020-11-07 | GCard System | Offline Points | 0 | 2020-11-07 | 2020-11-07 | Review validation for already encoded entry
2020-11-07 | GCard System | Points Update | 0 | 2020-11-07 | 2020-11-07 | Removed QR Code OTP Validation on offline verification for digital type GCARD
2020-11-09 | FB Promo | Utility to auto-send transaction encoded for raffle | 1 | 2020-11-11 | 2020-11-14 | Sent to implementation team for testing
2020-11-09 | FB Promo | Add address entry on interface | 1 | 2020-11-09 | 2020-11-10 | Encounted cursor error on search feature for SQLite
2020-11-10 | appdriver-agent-fx-ui | Added browsing using JSON Array as Datasource | 0 | 2020-11-10 | 2020-11-10
2020-11-12 | Task | Test update of MP Financing app compiled as Lender.exe @ Samsung Vigan | 0 | 2020-11-12 | 2020-11-12 | MP Branches financing system is not updating when we update dlls and exe because of different directory. Will inform implementor/support to place the system on vb.net folder of GGC_Systems
2020-11-12 | PETMgr | Trace program why some employees are not appearing on contact tracing | 0 | 2020-11-12 | 2020-11-12 | The employee has no barangay id assigned.
2020-11-12 | Task | Install TAP to Ars HR | 0 | 2020-11-12 | 2020-11-12 | Request access at home to open system
2020-11-14 | Lender | Allow searching of account number on CC reference on API Payments | 1 | 2020-11-14 | 2020-11-16 | On-hold, because Sir Jeff and Jovan team is developing Cartrade Credit App wherein it is the same location of object for API Partner Payments
2020-11-16 | Task | Check MCC Bani reporting PR Payments are not reflecting on main office | 0 | 2020-11-16 | 2020-11-16 | As of checking the payments reported are appearing on ledger. Asking them to verify to collection dept what is actually they are looking for
2020-11-16 | Utility | API Payment Utility | 0 | 2020-11-16 | 2020-11-16 | Classify and consolidate JAVA utility to one object and prepare to LINUX crontab usage
2020-11-16 | Utility | Client Mobile Utility | 0 | 2020-11-16 | 2020-11-16 | Classify and consolidate JAVA utility to one object and prepare to LINUX crontab usage
2020-11-16 | Utility | TLM Priority Leads | 0 | 2020-11-16 | 2020-11-16 | Classify and consolidate JAVA utility to one object and prepare to LINUX crontab usage
2020-11-16 | Utility | TLM MC Sales to MP Leads | 0 | 2020-11-16 | 2020-11-16 | Classify and consolidate JAVA utility to one object and prepare to LINUX crontab usage
2020-11-16 | Utility | TLM MC Credit Application to Leads | 0 | 2020-11-16 | 2020-11-16 | Classify and consolidate JAVA utility to one object and prepare to LINUX crontab usage
IntegSys

## TDD
testObject |  |  | name of the object
| declare static variable |  | declaration
| declare variable |  | declaration
| @BeforeAll |  | a procedure that is called once when the object was used
public static void setupClass()
| @BeforeEach |  | a procedure that is always executing on every before a test method was executed
public void setupTest()
| @AfterEach |  | a procedure that is always executing on every after a test method was executed
public void tearDownTest()
| @AfterAll |  | a procedure thas is called once when the object use ended
public static void tearDownClass()
| @Test |  | test method
public void testMethod1
| @Test |  | test method
public void testMethod2
AssetJ |  | AssertThat
Hamcrest |  | AssertThat, Matcher
Mocking Frameworks
jMock
Mockito
EasyMock

## ACEN
ACEN |  | PER(%) |  | Assumption after SRO |  | Stock Price
Outstanding | 13692457210 | 85.7921 |  | Outstanding * Current Price | 123232114890 | 2020-11-20 | Current Price | 9
SRO | 2267580434 | 14.2079 |  | SRO Shares * SRO Price | 5374165628.58 |  | SRO Price | 2.37
Total After | 15960037644 | 100 | --> | Price After SRO | 8.058 | after SRO | GIC Investment | 2.97 | 17.5 ownership
Holdings |  | PER(%) |  | SRO Allotment | Amount
COL | 13000 | 100 |  | 11711.7117 | 26070
FMSec | 0 | 0 |  | 0 | 0
Total | 13000 | 100 |  | 49000 | 26070
|  |  |  | Capitalization | Stock Price
|  |  |  | 123232114890 | 9 | --------> | Current market capitalization
|  |  |  | 90000000000 | 5.6391 | --------> | Projected by management to have 90B Market Cap on YYYY
|  |  |  | Assumption after GIC Investment |  | --------> | Partial analysis
|  |  |  | Outstanding Shares | 15960037644
|  |  |  | Shares to acquire | 4000000000
|  |  |  | GIC Acquired | 11880000000 | --------> | Remaining from 20B will be given to AC
since AC since AC Energy is 100% owned by AC
8120000000
[5 empty] | 16685800533 | --------> | AC through AC Energy will receive
ACEN shares in exchange for its international power and energy assets.
That is on top of its existing controlling shares in ACEN.
Current Holding
|  |  |  | Current Portfolio Value | 117000
|  |  |  | Current Portfolio Value after SRO | 104754.2421
|  |  |  | Difference | -12245.7579
SRO Subscription
|  |  |  | Subsbription Amount | 26070
|  |  |  | Value after SRO | 88638.2048
|  |  |  | Difference | 62568.2048

## Sheet2
2020-02-01
| Incentive | Deduct | Net
Xavier | 3406.1 | 0 | 3406.1
Jayson | 1946.34 | 2000 | -53.66
Kenneth | 1216.46 | 0 | 1216.46
4568.9