## Summary
Project Implementation
|  |  | Target |  |  |  | Actual |  |  |  |  | STATUS KEY | PRIORITY KEY | Assignee
STATUS | PRIORITY | TASK NAME | DUE DATE | START DATE | END DATE | DURATION | Assigned to | Remarks | % DONE | Date Started | Accomplished | On Hold | Low | Sheryl
In Progress | Medium | Hotline Incoming |  | 2018-08-27 | 2018-08-31 | 4 | Mac | c/o mac | 50% |  |  | On Que | Medium | Shanley
In Progress | High | Petty Cash |  | 2018-09-10 | 2018-09-14 | 4 | Sheryl | Implemented to audit dept & accounting | 0% |  |  | In Progress | High | Mac
On Que | Medium | DashBoard - Xavier |  | 2018-09-11 | 2018-09-20 | 9 | Shanley | Ready to transfer | 5% |  |  | Cancelled |  | TJ
Completed | High | 2H Production System |  | 2018-09-04 | 2018-09-08 | 4 | Shanley | shan & she. | 75% |  |  | Completed
Completed | Medium | Guanzon Parcel |  | 2018-09-04 | 2018-09-15 | 11 | Shanley | shan & she. | 100%
On Que | Medium | MP Cluster Delivery |  | 2018-06-01 | 2018-09-06 | 95 | Sheryl | for implementation - GMO | 0%
On Que | Medium | MC Cluster Delivery |  | 2018-09-04 | 2018-09-08 | 4 | Shanley | for implementation - GMO | 0%
On Hold | Medium | Guanzon Car Trade |  | 11/20/2018 | 11/20/2018 | 1 | Shanley | my mga changes pa. need to discuss sa meeting | 0%
On Que | High | Query Manager FX |  | 2018-09-06 | 2018-09-08 | 2 | Sheryl | New query manager | 0%
On Que | High | System User Manager FX |  | 2018-09-06 | 2018-09-08 | 2 | Sheryl | New sysuser | 0%
On Que | High | General Purchasing FX |  | 2018-09-10 | 2018-09-15 | 5 | Sheryl | General Purchasing for Monarch; Shanley | 0%
On Hold | Medium | Supplies Inventory |  | 2018-09-11 | 2018-09-20 | 9 | Shanley | ask sir jheff. | 0%
On Hold | Low | Asset System - without serial |  | 2018-09-10 | 2018-09-14 | 4 | Shanley | wala pang adjustment. C/O S'jheff | 0%
In Progress | Low | General Transfer |  | 2018-09-04 | 2018-10-06 | 32 | Shanley | implemented to all dept. | 90%
Completed | Low | TELECOM - CREDIT CARD(Accessories) |  | 2018-09-10 | 2018-09-14 | 4 | Shanley |  | 100%
On Hold | Low | MP PO to Supplier |  | 2018-09-10 | 2018-09-14 | 4 | Shanley |  | 0%
In Progress | Low | Webcam |  | 2018-09-10 | 2018-09-14 | 4 | Shanley |  | 80%
In Progress | High | System Update - All Application |  | 2018-09-10 | 2018-09-14 | 4 | Shanley |  | 0%
In Progress | High | SP Inventory Count - IntegSys |  |  |  | 0 | Shanley | calasiao & dagupan area | 50%
Completed | High | CI Approval Code - Android |  | 2019-02-25 | 2019-03-25 | 30 | Mac |  | 100%
Completed | High | In House Financing - MP |  | 2019-01-01 | 2019-01-01 | 0 | Shanley |  | 100%
Completed | High | Knox Guard |  | 2019-01-09 | 2019-01-09 | 0 | Shanley |  | 100%
On Que | High | Winows + G |  |  |  | 0 | Shanley |  | 0%
On Que | High | UnEncoded Transaction(s) |  |  |  | 0 | Shanley |  | 0%
In Progress | High | Pedritos Food Software |  | 2019-05-14 | 2019-06-14 | 30 | Mac | Used for charge invoice only; TJ | 95%
In Progress | High | General Inventory(Food) |  | 2019-05-18 | 2019-06-18 | 30 | Mac | Capturing inventory from list given by LP Admin | 50%
In Progress | High | Payroll System(Engr) |  | 2019-05-24 | 2019-06-24 | 30 | Mac |  | 0%
In Progress | High | Inventory & Purchasing(Engr) |  | 2019-05-27 | 2019-06-27 | 30 | Mac |  | 0%
Cancelled | Low | SP Purchase Order Posting |  |  |  | 0 |  | Abort mission | 100%
In Progress | Low | Delivery Schedule |  |  |  | 0 |  |  | 0%
In Progress | Low | Delivery Monitoring |  |  |  | 0 |  |  | 0%
On Que | Low | Cartrade: Account Entry |  |  |  | 0 |  |  | 0%
On Que | Low | Catrade: Billing |  |  |  | 0 |  |  | 0%
In Progress | Low | Document Transfer |  |  |  | 0 |  |  | 50%
In Progress | Low | Guanzon Apps |  |  |  | 0 |  |  | 0%
On Que | Low | MC Transfer Approval Code |  |  |  | 0 | Mac | Waiting for activation; transferred to all branches | 0%
Completed | Low | Payroll System(Cars) |  |  |  | 0 | Sheryl |  | 50%
On Que | Low | Branches 2nd Unit Activation |  |  |  | 0 | Sheryl | c/o SSG | 100%
In Progress | Low | Master Slave Replication |  |  |  | 0 | Sheryl |  | 2%
Completed | Low | Log-in to Other Branch |  |  |  | 0 | Sheryl |  | 95%
On Que | Low | E-commerce |  |  |  | 0 |  |  | 0%
On Que | Low | Guanzon Website as Main Page |  |  |  | 0 |  |  | 5%
On Que | Low | MC Insurance Payment for AP Payment |  |  |  | 0 | Sheryl |  | 100%
Completed | Low | Timekeeper Update for Monarch |  | 2019-05-11 | 2019-05-15 | 4 | Mac |  | 100%
On Que | Low | Meal Voucher |  |  |  | 0 |  | Waiting for POS Printer | 0%
Note on D4: Please put all for implementation module here and propose a target for our monitoring. Implementation of Branch System must be included to for us to monitor that load of per implementor -rex adversalo

## Detail
MOTORCYCLE | Area 1 (MC) | Area 2 (MC) | Area 3 (MC) | Area 4 (MC) | Area 5 (MC) | Area 6 (MC) | Area 7 (MC) | Area 8 (MC) | Area 9 (MC) | Area 10 (MC) | Area 11 (MC) | Area 12 (MC) | Area 13 (MC)
INTEGSYS |  |  | IMP. DATE |  | IMP. DATE
WebCam - Application Entry |  |  | 2018-10-24 |  | 2018-10-26
Petty Cash |  |  | 2018-10-24 |  | 2018-10-26
SP Inventory Count |  |  | 2018-10-24 |  | 2018-10-26
Document Transfer |  |  | 2018-10-24 |  | 2018-10-26
Deposit Slip Form - New Format |  |  | 2018-10-24 |  | 2018-10-26
Unencoded Transaction
CI Approval code
Reports Request |  |  | IMP. DATE |  | IMP. DATE
MC PO Receiving |  |  | 2018-10-24 |  | 2018-10-26
SP PO Receiving |  |  | 2018-10-24 |  | 2018-10-26
SureTrack Summary Report |  |  | 2018-10-24 |  | 2018-10-26
Petty Cash report |  |  | 2018-10-24 |  | 2018-10-26
SP Transaction Summary(UNION SP History Ledger) |  |  | 2018-10-24 |  | 2018-10-26
MC Sales & Inventory Summary
MOBILE PHONE | Area 1 (MP) | Area 2 (MP) | Area 3 (MP) | Area 4 (MP) | Area 5 (MP)
TELECOM | IMP. DATE
In House Finance - North Point | 10-17-2018
Petty Cash | 2017-01-10
Document Transfer | 2017-01-10
Deposit Slip Form - New Format
Note on B21: Metro Dagupan Only -sheryl rabanal