## Sheet1
|  |  |  | MIS Timeline |  |  | Management Timeline
Priority | Type | Project Code | Project Name | Desktop | Mobile | Total | Desktop | Mobile | Total
1 | Desktop | 70240000 | Health Checklist App | 8 | 0 | 8 | 12 | 0 | 12
2 | Mobile | 70010000 | Collection(DCP) | 0 | 20 | 20 | 0 | 30 | 30
3 | Desktop | 10010000 | Engineering Inventory Management System | 30 | 0 | 30 | 45 | 0 | 45
4 | Desktop | 40010000 | Los Pedritos Integrated Systems | 60 | 0 | 60 | 90 | 0 | 90
5 | Desktop | 20010000 | 2H MC Pricelist | 15 | 0 | 15 | 23 | 0 | 23
6 | Desktop | 60010000 | Online Credit Application | 6 | 0 | 6 | 6 | 0 | 6
7 | Desktop | 60020000 | Online Employment Application | 6 | 0 | 6 | 6 | 0 | 6
8 | Desktop | 60030000 | Link HCM with Online Application from Website/Android | 5 | 0 | 5 | 8 | 0 | 8
9 | Mobile | 70020000 | Integration of Telecom and IntegSys | 0 | 15 | 15 | 0 | 23 | 23
10 | Mobile | 70030000 | Credit Investigation | 0 | 15 | 15 | 0 | 23 | 23
11 | Desktop | 20020000 | Incorporate DP Discount on MC Sales for installed Guanzon App | 2 | 8 | 10 | 3 | 12 | 15
12 | Desktop | 20030000 | Require OTP on releasing giveaways on MC Sales | 5 | 0 | 5 | 8 | 0 | 8
13 | Desktop | 10020000 | Recurring Expenses | 8 | 0 | 8 | 12 | 0 | 12
14 | Desktop | 20040000 | Incorporate rebate coupon for every service(Service rebate coupon) | 5 | 0 | 5 | 8 | 0 | 8
15 | Mobile | 70040000 | Online Credit App - Applicant photo capture | 0 | 10 | 10 | 0 | 15 | 15
16 | Mobile | 70050000 | Selfie Login | 0 | 8 | 8 | 0 | 12 | 12
17 | Mobile | 70060000 | Online Credit App - Document scanning | 0 | 15 | 15 | 0 | 23 | 23
18 | Desktop | 20050000 | Branch efficiency to be monitored by selling branch not collecting branch | 3 | 0 | 3 | 5 | 0 | 5
19 | Desktop | 20060000 | Monitoring of approved applications pending sales | 2 | 0 | 2 | 3 | 0 | 3
20 | Desktop | 20070000 | Adjust telemarketing approved credit application retreival to 3 days | 1 | 0 | 1 | 2 | 0 | 2
21 | Mobile | 70070000 | Daily Branch Opening Notification | 0 | 8 | 8 | 0 | 12 | 12
22 | Desktop | 20080000 | Incorporate duration of special promo rebates on encoding MC Sales | 5 | 0 | 5 | 8 | 0 | 8
23 | Desktop | 10030000 | Integrated Replication For Multiple Database | 10 | 0 | 10 | 15 | 0 | 15
24 | Mobile | 70080000 | Attendance summary Notification | 0 | 10 | 10 | 0 | 15 | 15
25 | Mobile | 70090000 | Service Hotline | 0 | 10 | 10 | 0 | 15 | 15
26 | Mobile | 70100000 | Branch Performance Monitoring | 0 | 10 | 10 | 0 | 15 | 15
27 | Desktop | 10040000 | MP Consignment Payment | 5 | 0 | 5 | 8 | 0 | 8
28 | Mobile | 70110000 | 360 Evaluation | 0 | 15 | 15 | 0 | 23 | 23
29 | Desktop | 10050000 | Integrate MC/MP Purchase Order thru General Accounting System | 8 | 0 | 8 | 12 | 0 | 12
30 | Desktop | 20090000 | Separate BNOS sales and inventory of 2H shops | 3 | 0 | 3 | 5 | 0 | 5
31 | Desktop | 10060000 | Advance Payment/COD Monitoring | 6 | 0 | 6 | 9 | 0 | 9
32 | Mobile | 70120000 | Leave, OB, etc entry for managers/supervisors | 0 | 20 | 20 | 0 | 30 | 30
33 | Desktop | 10070000 | 201 File Update | 3 | 0 | 3 | 5 | 0 | 5
34 | Mobile | 70130000 | Payslip | 0 | 10 | 10 | 0 | 15 | 15
35 | Desktop | 10080000 | Text notification for Pay Slip of Monarch engineering workers | 3 | 0 | 3 | 5 | 0 | 5
36 | Desktop | 10090000 | Payroll Encryption System | 5 | 0 | 5 | 8 | 0 | 8
37 | Desktop | 10100000 | Approval Code (S' Jo, S' Guan, S' Arnold) | 6 | 0 | 6 | 9 | 0 | 9
38 | Desktop | 10110000 | Random Sending of Pay Slip | 15 | 0 | 15 | 23 | 0 | 23
39 | Desktop | 20100000 | FSC & WRC Report | 4 | 0 | 4 | 6 | 0 | 6
40 | Desktop | 10120000 | IOM Issuance | 15 | 0 | 15 | 23 | 0 | 23
41 | Desktop | 20110000 | Change Unit, Name, Address Monitoring(Reports) | 3 | 0 | 3 | 5 | 0 | 5
42 | Desktop | 20120000 | Warranty Claims Report | 4 | 0 | 4 | 6 | 0 | 6
43 | Desktop | 10130000 | Midtier Utility Between Cervo and Pedritos Systems | 30 | 0 | 30 | 45 | 0 | 45
44 | Desktop | 10140000 | Payroll Reports | 8 | 0 | 8 | 12 | 0 | 12
45 | Desktop | 10150000 | Midtier Utility Between Telecom POS and Telecom | 20 | 0 | 20 | 30 | 0 | 30
46 | Desktop | 10160000 | Midtier Utility Between IntegSys POS and IntegSys | 20 | 0 | 20 | 30 | 0 | 30
47 | Desktop | 40020000 | Management Report (Pedritos Integrated Systems) | 30 | 0 | 30 | 45 | 0 | 45
48 | Mobile | 70140000 | Notification/Messaging | 0 | 15 | 15 | 0 | 23 | 23
49 | Mobile | 70150000 | Notification/Messaging | 0 | 10 | 10 | 0 | 15 | 15
50 | Desktop | 60040000 | Advance Payment thru Gcash | 10 | 0 | 10 | 10 | 0 | 10
51 | Mobile | 70160000 | Advance Payment thru GCash - LINK TO WEBSITE | 0 | 10 | 10 | 0 | 15 | 15
52 | Mobile | 70170000 | Pre-term Computaion | 0 | 8 | 8 | 0 | 12 | 12
53 | Desktop | 60050000 | Pre-Order Sales(Parts/Unit Ordering) | 10 | 0 | 10 | 10 | 0 | 10
54 | Mobile | 70180000 | Parts/Unit Ordering - LINK TO WEBSITE | 0 | 10 | 10 | 0 | 15 | 15
55 | Mobile | 70190000 | Service Scheduling | 0 | 10 | 10 | 0 | 15 | 15
56 | Mobile | 70200000 | Cash Count | 0 | 15 | 15 | 0 | 23 | 23
57 | Mobile | 70210000 | Approvals | 0 | 8 | 8 | 0 | 12 | 12
58 | Mobile | 70220000 | Reimbursement | 0 | 10 | 10 | 0 | 15 | 15
59 | Mobile | 70230000 | Random Stock Inventory | 0 | 10 | 10 | 0 | 15 | 15
60 | Mobile | 60060000 | Online Credit Application - LINK TO WEBSITE | 0 | 10 | 10 | 0 | 15 | 15
61 | Mobile | 60070000 | Online Employment Application - LINK TO WEBSITE | 0 | 10 | 10 | 0 | 15 | 15
97 | Desktop | 60080000 | Event schedules and service reminders | 45 | 0 | 45 | 45 | 0 | 45
98 | Desktop | 10170000 | Text notification for employee applications(Receipt of application, Rejection) | 3 | 0 | 3 | 5 | 0 | 5
100 | Desktop | 10180000 | General Services App | 15 | 0 | 15 | 23 | 0 | 23
100 | Mobile | 70250000 | General Services App | 0 | 40 | 40 | 0 | 60 | 60
|  |  |  | 434 | 340 | 774 | 621 | 513 | 1134

## Sheet2
Project Code | Project Description | Parent Code
10000000 | Main Office
10010000 | Engineering Inventory Management System | 10000000
10020000 | Recurring Expenses | 10000000
10030000 | Integrated Replication For Multiple Database | 10000000
10040000 | MP Consignment Payment | 10000000
10050000 | Integrate MC/MP Purchase Order thru General Accounting System | 10000000
10060000 | Advance Payment/COD Monitoring | 10000000
10070000 | 201 File Update | 10000000
10080000 | Text notification for Pay Slip of Monarch engineering workers | 10000000
10090000 | Payroll Encryption System | 10000000
10100000 | Approval Code (S' Jo, S' Guan, S' Arnold) | 10000000
10110000 | Random Sending of Pay Slip | 10000000
10120000 | IOM Issuance | 10000000
10130000 | Midtier Utility Between Cervo and Pedritos Systems | 10000000
10140000 | Payroll Reports | 10000000
10150000 | Midtier Utility Between Telecom POS and Telecom | 10000000
10160000 | Midtier Utility Between IntegSys POS and IntegSys | 10000000
10170000 | Text notification for employee applications(Receipt of application, Rejection) | 10000000
10180000 | General Services App | 10000000
10190000 | Purchsing Approval(Engrs, S' Jo, S' Guan) - 2020 | 10000000
10200000 | Facebook Like Promo - 2020 | 10000000
10210000 | Disbursement(Detailed) - 2020 | 10000000
10220000 | General Journal - 2020 | 10000000
10230000 | Petty Cash (Engineering) - 2020 | 10000000
10240000 | MP/MC Credit Application - 2020 | 10000000
20000000 | MC Division
20010000 | 2H MC Pricelist | 20000000
20020000 | Incorporate DP Discount on MC Sales for installed Guanzon App | 20000000
20030000 | Require OTP on releasing giveaways on MC Sales | 20000000
20040000 | Incorporate rebate coupon for every service(Service rebate coupon) | 20000000
20050000 | Branch efficiency to be monitored by selling branch not collecting branch | 20000000
20060000 | Monitoring of approved applications pending sales | 20000000
20070000 | Adjust telemarketing approved credit application retreival to 3 days | 20000000
20080000 | Incorporate duration of special promo rebates on encoding MC Sales | 20000000
20090000 | Separate BNOS sales and inventory of 2H shops | 20000000
20100000 | FSC & WRC Report | 20000000
20110000 | Change Unit, Name, Address Monitoring(Reports) | 20000000
20120000 | Warranty Claims Report | 20000000
20130000 | Notification for Collecting & Selling Branch - 2020 | 20000000
20140000 | Collection Effeciency Monitoring thru DCP - 2020 | 20000000
20150000 | Add Branch Inquiry searching in Customer Order - 2020 | 20000000
20160000 | Allocate Inventory for SP Customer Order - 2020 | 20000000
20170000 | POS like Barcode Reading - 2020 | 20000000
20180000 | Collection Monitoring(monitored by branch) - 2020 | 20000000
20190000 | Rebate Escalation - 2020 | 20000000
30000000 | MP Division
30010000 | MP Purchasing via eMail | 30000000
40000000 | Los Pedritos
40010000 | Los Pedritos Integrated Systems | 40000000
40020000 | Management Report (Pedritos Integrated Systems) | 40000000
40030000 | POS - Food - 2020 | 40000000
50000000 | AutoGroup
50010000 | Cartrade Credit Application - 2020 | 50000000
60000000 | Website
60010000 | Online Credit Application | 60000000
60020000 | Online Employment Application | 60000000
60030000 | Link HCM with Online Application from Website/Android | 60000000
60040000 | Advance Payment thru Gcash | 60000000
60050000 | Pre-Order Sales(Parts/Unit Ordering) | 60000000
60060000 | Online Credit Application - LINK TO WEBSITE | 60000000
60070000 | Online Employment Application - LINK TO WEBSITE | 60000000
60080000 | Event schedules and service reminders | 60000000
70000000 | Android App
70010000 | Collection (DCP) | 70000000
70020000 | Integration of Telecom and IntegSys | 70000000
70030000 | Credit Investigation | 70000000
70040000 | Online Credit App - Applicant photo capture | 70000000
70050000 | Selfie Login | 70000000
70060000 | Online Credit App - Document scanning | 70000000
70070000 | Daily Branch Opening Notification | 70000000
70080000 | Attendance summary Notification | 70000000
70090000 | Service Hotline | 70000000
70100000 | Branch Performance Monitoring | 70000000
70110000 | 360 Evaluation | 70000000
70120000 | Leave, OB, etc entry for managers/supervisors | 70000000
70130000 | Payslip | 70000000
70140000 | Notification/Messaging | 70000000
70150000 | Notification/Messaging | 70000000
70160000 | Advance Payment thru GCash - LINK TO WEBSITE | 70000000
70170000 | Pre-term Computaion | 70000000
70180000 | Parts/Unit Ordering - LINK TO WEBSITE | 70000000
70190000 | Service Scheduling | 70000000
70200000 | Cash Count | 70000000
70210000 | Approvals | 70000000
70220000 | Reimbursement | 70000000
70230000 | Random Stock Inventory | 70000000
70240000 | Health Checklist App | 70000000
70250000 | General Services App | 70000000

## Sheet3
Auto App
Inventory
Sales
Registration
Disbursement
AR
Parts

## Codes
Project Code | Project Description | Parent Code
10000000 | Main Office
10100000 | Human Capital Management | 10000000
10101000 | 201 File Update | 10100000
10102000 | IOM Issuance | 10100000
10103000 | Payroll Encryption System | 10100000
10104000 | Random Sending of Pay Slip | 10100000
10200000 | Credit Support Services | 10000000
10300000 | Facility & Security Management | 10000000
10400000 | Supply Chain Management | 10000000
10500000 | Marketing & Promotions | 10000000
10600000 | Management Information System | 10000000
10700000 | After Sales Management | 10000000
10800000 | Finance Management | 10000000
10801000 | General Services | 10800000
10801000 | Recurring Expenses | 10800000
10802000 | Payroll Reports | 10800000
10803000 | MP Consignment Payment | 10800000
10804000 | Advance Payment/COD Monitoring | 10800000
10805000 | Integrate MC/MP Purchase Order thru General Accounting System | 10800000
10900000 | Record Depository | 10000000
11000000 | Duty & Requisites Services | 10000000
11100000 | Pre-Owned Management | 10000000
11102000 | 2H MC Pricelist(Individual) | 11100000
11103000 | 2H MC Pricelist(Lot Sale) | 11100000
11200000 | Engineering Services | 10000000
11201000 | Engineering Inventory Management System | 11200000
11300000 | Procurement Services | 10000000
11400000 | Compliance Management | 10000000
11500000 | Telemarketing Management | 10000000
11600000 | Cellphone Warehouse | 10000000
20000000 | MC Division
20100000 | GMC IntegSys | 20000000
20200000 | G-Card System | 20000000
20300000 | Lender | 20000000
30000000 | MP Division
30100000 | Telecom | 30000000
30200000 | Lender | 30000000
40000000 | Los Pedritos
40100000 | POS System | 40000000
40100000 | LP IntegSys | 40000000
50000000 | AutoGroup
60000000 | Website
60101000 | General Features
60101000 | Pre-Order Sales(Parts/Unit Ordering) | 60000000
60102000 | Online Credit Application | 60000000
60103000 | Online Employment Application | 60000000
60104000 | Payment thru Gcash | 60000000
70000000 | Android App
70100000 | Credit Support Services | 70000000
70101000 | Online Credit Application | 70100000
70101001 | Documment Scanning | 70101000
70101002 | Applicant Photo Capturing | 70101000
70102000 | Daily Collection Plan | 70100000
70103000 | Credit Investigation | 70100000
70200000 | Human Capital Management | 70000000
70201000 | Selfie Login | 70200000
70202000 | Leave, OB, etc entry for managers/supervisors | 70200000
70203000 | Attendance summary Notification | 70200000
70204000 | Health Checklist App | 70200000
70205000 | Payslip | 70200000
70206000 | 360 Evaluation | 70200000
70300000 | Finance Management | 70000000
70301000 | General Services App | 70300000
70302000 | Reimbursement | 70300000
70400000 | Compliance Management | 70000000
70401000 | Cash Count | 70400000
70402000 | Random Stock Inventory | 70400000
70500000 | Area Head | 70000000
70501000 | Branch Performance Monitoring | 70500000
70502000 | Daily Branch Opening Notification | 70500000
70600000 | General Features(Employee) | 70000000
70601000 | Approvals | 70600000
70602000 | Notification/Messaging | 70600000
70700000 | General Features(Customer) | 70000000
70701000 | Notification/Messaging | 70700000
70702000 | Service Hotline | 70700000
70703000 | Parts/Unit Ordering - LINK TO WEBSITE | 70700000
70704000 | Payment thru GCash - LINK TO WEBSITE | 70700000
70705000 | Online Credit Application - LINK TO WEBSITE | 70700000
70706000 | Online Employment Application - LINK TO WEBSITE | 70700000
70800000 | Credit Support Services | 70000000
70801000 | Pre-term Computaion | 70800000
70900000 | After Sales Management | 70000000
70901000 | Service Scheduling | 70900000

## Projects
Priority | New | Request By | Type | Type | Client | Code | Project Name | Est. Days | Desktop | Android | Website | Desktop F | Android F
| 1 | S'Rex | Mobile | Android | Employee | 70102000 | Collection(DCP) | 20 |  | 20 |  | 0 | 30
| 2 | S'Guan | Desktop | Desktop | ES | 11201000 | Engineering Inventory Management System | 30 | 30 |  |  | 45 | 0
16 | 3 | S'Rex | Desktop | Desktop | LP | 40100000 | Los Pedritos Integrated Systems | 60 | 60 |  |  | 90 | 0
4 | 4 | S'Guan | Desktop | Desktop | 2H | 11102000 | 2H MC Pricelist | 15 | 15 |  |  | 23 | 0
1 | 5 |  | Desktop | Website | MC/MP | 60102000 | Online Credit Application | 6 |  |  | 6 | 0 | 0
2 | 6 |  | Desktop | Website | HCM | 60103000 | Online Employment Application | 6 |  |  | 6 | 0 | 0
3 | 7 | 2021 | Desktop | Desktop | Desktop |  | Link HCM with Online Application from Website/Android | 5 | 5 |  |  | 8 | 0
8 |  | 2021 |  | Deferred | Desktop |  | CR Inventory for Service Vehicle | 10 | 10
5 | 8 | 2021 | Mobile | Android | Android |  | Integration of Telecom and IntegSys | 15 |  | 15 |  | 0 | 23
7 | 9 | S'Rex | Mobile | Android | Employee | 70103000 | Credit Investigation | 15 |  | 15 |  | 0 | 23
9 | 10 | S'Jo | Desktop | Strat | Android/Desktop |  | Incorporate DP Discount on MC Sales for installed Guanzon App | 10 | 2 | 8 |  | 3 | 12
11 | 11 | S'Jo | Desktop | Strat | Desktop/API |  | Require OTP on releasing giveaways on MC Sales | 5 | 5 |  |  | 8 | 0
6 | 12 |  | Desktop | Desktop | FM | 10801000 | Recurring Expenses | 8 | 8 |  |  | 12 | 0
13 | 13 | S'Jo | Desktop | Strat | Desktop |  | Incorporate rebate coupon for every service(Service rebate coupon) | 5 | 5 |  |  | 8 | 0
9 | 14 |  | Mobile | Android | Employee | 70101002 | Online Credit App - Applicant photo capture | 10 |  | 10 |  | 0 | 15
12 | 15 | S'Jo | Mobile | Android | Employee | 70201000 | Selfie Login | 8 |  | 8 |  | 0 | 12
10 | 16 |  | Mobile | Android | Employee | 70101001 | Online Credit App - Document scanning | 15 |  | 15 |  | 0 | 23
15 | 17 | S'Rex | Desktop | Strat | Desktop/Report |  | Branch efficiency to be monitored by selling branch not collecting branch | 3 | 3 |  |  | 5 | 0
18 | 18 | S'Rex | Desktop | Strat | Desktop/Report |  | Monitoring of approved applications pending sales | 2 | 2 |  |  | 3 | 0
20 |  | 2021 |  | Deferred | Desktop |  | CR Inventory for Cash Loan | 8
22 | 19 | S'Jo | Desktop | Strat | Utility |  | Adjust telemarketing approved credit application retreival to 3 days | 1 | 1 |  |  | 2 | 0
17 | 20 |  | Mobile | Android | Employee | 70502000 | Daily Branch Opening Notification | 8 |  | 8 |  | 0 | 12
24 | 21 |  | Desktop | Strat |  |  | Incorporate duration of special promo rebates on encoding MC Sales | 5 | 5 |  |  | 8 | 0
19 | 22 | 2021 | Desktop | Utilities | Utility |  | Integrated Replication For Multiple Database | 10 | 10 |  |  | 15 | 0
21 | 23 |  | Mobile | Android | Employee | 70203000 | Attendance summary Notification | 10 |  | 10 |  | 0 | 15
25 | 24 | S'Rex | Mobile | Android | Customer | 70702000 | Service Hotline | 10 |  | 10 |  | 0 | 15
26 |  | 2020 |  | Deferred | Desktop |  | MP Inventory Count | 12
23 | 25 |  | Mobile | Android | Employee | 70501000 | Branch Performance Monitoring | 10 |  | 10 |  | 0 | 15
26 | 26 |  | Desktop | Desktop | FM | 10803000 | MP Consignment Payment | 5 | 5 |  |  | 8 | 0
27 | 27 |  | Mobile | Android | Employee | 70206000 | 360 Evaluation | 15 |  | 15 |  | 0 | 23
28 | 28 |  | Desktop | Desktop | FM | 10805000 | Integrate MC/MP Purchase Order thru General Accounting System | 8 | 8 |  |  | 12 | 0
29 | 29 |  | Desktop | Strat | Desktop |  | Separate BNOS sales and inventory of 2H shops | 3 | 3 |  |  | 5 | 0
31 | 30 |  | Desktop | Desktop | FM | 10804000 | Advance Payment/COD Monitoring | 6 | 6 |  |  | 9 | 0
31 | 31 |  | Mobile | Android | Employee | 70202000 | Leave, OB, etc entry for managers/supervisors | 20 |  | 20 |  | 0 | 30
32 | 32 |  | Desktop | Desktop | HCM | 10101000 | 201 File Update | 3 | 3 |  |  | 5 | 0
32 | 33 |  | Mobile | Android | Employee | 70205000 | Payslip | 10 |  | 10 |  | 0 | 15
33 | 34 | S'Jo | Desktop | Strat | Desktop |  | Text notification for Pay Slip of Monarch engineering workers | 3 | 3 |  |  | 5 | 0
34 | 35 |  | Desktop | Desktop | HCM | 10103000 | Payroll Encryption System | 5 | 5 |  |  | 8 | 0
34 | 36 | 2020 | Desktop | Desktop | Android |  | Approval Code (S' Jo, S' Guan, S' Arnold) | 6 | 6 |  |  | 9 | 0
35 | 37 |  | Desktop | Desktop | HCM | 10104000 | Random Sending of Pay Slip | 15 | 15 |  |  | 23 | 0
36 | 38 | 2020 | Desktop | Desktop | Desktop |  | FSC & WRC Report | 4 | 4 |  |  | 6 | 0
37 | 39 |  | Desktop | Desktop | HCM | 10102000 | IOM Issuance | 15 | 15 |  |  | 23 | 0
39 | 40 | 2020 | Desktop | Desktop | Desktop |  | Change Unit, Name, Address Monitoring(Reports) | 3 | 3 |  |  | 5 | 0
40 | 41 | 2020 | Desktop | Desktop | Desktop |  | Warranty Claims Report | 4 | 4 |  |  | 6 | 0
41 | 42 | 2021 | Desktop | Utilities | Utility |  | Midtier Utility Between Cervo and Pedritos Systems | 30 | 30 |  |  | 45 | 0
42 | 43 |  | Desktop | Desktop | FM | 10802000 | Payroll Reports | 8 | 8 |  |  | 12 | 0
| 44 | 2021 | Desktop | Utilities | Utility |  | Midtier Utility Between Telecom POS and Telecom | 20 | 20 |  |  | 30 | 0
| 45 | 2021 | Desktop | Utilities | Utility |  | Midtier Utility Between IntegSys POS and IntegSys | 20 | 20 |  |  | 30 | 0
| 46 | 2021 | Desktop | Desktop | Desktop |  | Management Report (Pedritos Integrated Systems) | 30 | 30 |  |  | 45 | 0
| 47 |  | Mobile | Android | Employee | 70602000 | Notification/Messaging | 15 |  | 15 |  | 0 | 23
| 48 |  | Mobile | Android | Customer | 70701000 | Notification/Messaging | 10 |  | 10 |  | 0 | 15
| 49 |  | Desktop | Website | MC/MP | 60104000 | Advance Payment thru Gcash | 10 |  |  | 10 | 0 | 0
| 50 | S'Guan | Mobile | Android | Customer | 70704000 | Advance Payment thru GCash - LINK TO WEBSITE | 10 |  | 10 |  | 0 | 15
| 51 |  | Mobile | Android | Customer | 70801000 | Pre-term Computaion | 8 |  | 8 |  | 0 | 12
| 52 | S'Rex | Desktop | Website | MC/MP | 60101000 | Pre-Order Sales(Parts/Unit Ordering) | 10 |  |  | 10 | 0 | 0
| 53 |  | Mobile | Android | Customer | 70703000 | Parts/Unit Ordering - LINK TO WEBSITE | 10 |  | 10 |  | 0 | 15
| 54 |  | Mobile | Android | Customer | 70901000 | Service Scheduling | 10 |  | 10 |  | 0 | 15
| 55 |  | Mobile | Android | Employee | 70401000 | Cash Count | 15 |  | 15 |  | 0 | 23
|  | S'Jo |  | Strat |  |  | Coordinate with mam lorane/sir jojo for 92 GPS not working(check if stator coil can be replaced)
|  | S'Jo |  | Strat |  |  | Purchase of OS security on company info
|  |  |  | Strat |  |  | Create/revise department orgaization structure
| 56 |  | Mobile | Android | Employee | 70601000 | Approvals | 8 |  | 8 |  | 0 | 12
| 57 |  | Mobile | Android | Employee | 70201000 | Reimbursement | 10 |  | 10 |  | 0 | 15
| 58 |  | Mobile | Android | Employee | 70402000 | Random Stock Inventory | 10 |  | 10 |  | 0 | 15
| 59 |  | Desktop | Desktop | Customer | 70705000 | Online Credit Application - LINK TO WEBSITE | 10 | 10 |  |  | 15 | 0
| 60 |  | Desktop | Desktop | Customer | 70706000 | Online Employment Application - LINK TO WEBSITE | 10 | 10 |  |  | 15 | 0
|  |  |  | Strat-Imp |  |  | Full implementation of DCP
|  | GMA |  | Strat-Imp |  |  | Re-train GMA office regarding MC Inventory aging at warehouses
|  |  |  | Strat-Imp |  |  | Full implementation of O-Guard
|  |  |  | Strat-Imp |  |  | Full implementation of DCP
|  | 2021 |  | Deferred | Desktop |  | Entry of Message to be auto masked
|  | 2020 |  | Deferred | Android |  | Reports thru web
| 97 | 2020 | Desktop | Website | Android |  | Event schedules and service reminders | 45 |  |  | 45 | 0 | 0
| 98 | S'Jo | Desktop | Strat | Desktop/API |  | Text notification for employee applications(Receipt of application, Rejection) | 3 | 3 |  |  | 5 | 0
| 99 | M'Carol | Mobile | Android | Employee | 70204000 | Health Checklist App | 8 |  | 8 |  | 0 | 12
| 100 | S'Jo | Desktop | Desktop | FM | 10801000 | General Services App | 15 | 15 |  |  | 23 | 0
|  | 2020 |  | Deferred | IntegSys |  | Activity Inquiry on Laptop
|  | 2020 |  | Deferred | IntegSys |  | Referral Incentive (G Card Points)
|  | 2020 |  | Deferred | IntegSys |  | System based Trade-in
|  | 2020 |  | Deferred | Report |  | Text Blast Report
|  | 2020 |  | Deferred | RIMS |  | Branch Inventory Posting (CR)
|  | 2020 |  | Deferred | Telecom |  | MP Trade In
|  | 2020 |  | Deferred | TeleMktg |  | Recording (BPO)
| 100 | S'Jo | Mobile | Android | Employee | 70301000 | General Services App | 40 |  | 40 |  | 0 | 60
[8 empty] | 812 | 387 | 328 | 77 | 574 | 495
[12 empty] | 265 | 186
Note on H14: Michael Cuison: Include all bills: PLDT/GLOBE/RENTAL. Automatic notification 10 days before due date.

## Final
New | Type | Project Name | Est. Days | Desktop | Android | Website | Desktop F | Android F
1 | Mobile | Collection(DCP) | 20 |  | 20 |  | 0 | 30
2 | Desktop | Engineering Inventory Management System | 30 | 30 |  |  | 45 | 0
3 | Desktop | Los Pedritos Integrated Systems | 60 | 60 |  |  | 90 | 0
4 | Desktop | 2H MC Pricelist | 15 | 15 |  |  | 23 | 0
5 | Desktop | Online Credit Application | 6 |  |  | 6 | 0 | 0
6 | Desktop | Online Employment Application | 6 |  |  | 6 | 0 | 0
7 | Desktop | Link HCM with Online Application from Website/Android | 5 | 5 |  |  | 8 | 0
8 | Mobile | Integration of Telecom and IntegSys | 15 |  | 15 |  | 0 | 23
9 | Mobile | Credit Investigation | 15 |  | 15 |  | 0 | 23
10 | Desktop | Incorporate DP Discount on MC Sales for installed Guanzon App | 10 | 2 | 8 |  | 3 | 12
11 | Desktop | Require OTP on releasing giveaways on MC Sales | 5 | 5 |  |  | 8 | 0
12 | Desktop | Recurring Expenses | 8 | 8 |  |  | 12 | 0
13 | Desktop | Incorporate rebate coupon for every service(Service rebate coupon) | 5 | 5 |  |  | 8 | 0
14 | Mobile | Online Credit App - Applicant photo capture | 10 |  | 10 |  | 0 | 15
15 | Mobile | Selfie Login | 8 |  | 8 |  | 0 | 12
16 | Mobile | Online Credit App - Document scanning | 15 |  | 15 |  | 0 | 23
17 | Desktop | Branch efficiency to be monitored by selling branch not collecting branch | 3 | 3 |  |  | 5 | 0
18 | Desktop | Monitoring of approved applications pending sales | 2 | 2 |  |  | 3 | 0
19 | Desktop | Adjust telemarketing approved credit application retreival to 3 days | 1 | 1 |  |  | 2 | 0
20 | Mobile | Daily Branch Opening Notification | 8 |  | 8 |  | 0 | 12
21 | Desktop | Incorporate duration of special promo rebates on encoding MC Sales | 5 | 5 |  |  | 8 | 0
22 | Desktop | Integrated Replication For Multiple Database | 10 | 10 |  |  | 15 | 0
23 | Mobile | Attendance summary Notification | 10 |  | 10 |  | 0 | 15
24 | Mobile | Service Hotline | 10 |  | 10 |  | 0 | 15
25 | Mobile | Branch Performance Monitoring | 10 |  | 10 |  | 0 | 15
26 | Desktop | MP Consignment Payment | 5 | 5 |  |  | 8 | 0
27 | Mobile | 360 Evaluation | 15 |  | 15 |  | 0 | 23
28 | Desktop | Integrate MC/MP Purchase Order thru General Accounting System | 8 | 8 |  |  | 12 | 0
29 | Desktop | Separate BNOS sales and inventory of 2H shops | 3 | 3 |  |  | 5 | 0
30 | Desktop | Advance Payment/COD Monitoring | 6 | 6 |  |  | 9 | 0
31 | Mobile | Leave, OB, etc entry for managers/supervisors | 20 |  | 20 |  | 0 | 30
32 | Desktop | 201 File Update | 3 | 3 |  |  | 5 | 0
33 | Mobile | Payslip | 10 |  | 10 |  | 0 | 15
34 | Desktop | Text notification for Pay Slip of Monarch engineering workers | 3 | 3 |  |  | 5 | 0
35 | Desktop | Payroll Encryption System | 5 | 5 |  |  | 8 | 0
36 | Desktop | Approval Code (S' Jo, S' Guan, S' Arnold) | 6 | 6 |  |  | 9 | 0
37 | Desktop | Random Sending of Pay Slip | 15 | 15 |  |  | 23 | 0
38 | Desktop | FSC & WRC Report | 4 | 4 |  |  | 6 | 0
39 | Desktop | IOM Issuance | 15 | 15 |  |  | 23 | 0
40 | Desktop | Change Unit, Name, Address Monitoring(Reports) | 3 | 3 |  |  | 5 | 0
41 | Desktop | Warranty Claims Report | 4 | 4 |  |  | 6 | 0
42 | Desktop | Midtier Utility Between Cervo and Pedritos Systems | 30 | 30 |  |  | 45 | 0
43 | Desktop | Payroll Reports | 8 | 8 |  |  | 12 | 0
44 | Desktop | Midtier Utility Between Telecom POS and Telecom | 20 | 20 |  |  | 30 | 0
45 | Desktop | Midtier Utility Between IntegSys POS and IntegSys | 20 | 20 |  |  | 30 | 0
46 | Desktop | Management Report (Pedritos Integrated Systems) | 30 | 30 |  |  | 45 | 0
47 | Mobile | Notification/Messaging | 15 |  | 15 |  | 0 | 23
48 | Mobile | Notification/Messaging | 10 |  | 10 |  | 0 | 15
49 | Desktop | Advance Payment thru Gcash | 10 |  |  | 10 | 0 | 0
50 | Mobile | Advance Payment thru GCash - LINK TO WEBSITE | 10 |  | 10 |  | 0 | 15
51 | Mobile | Pre-term Computaion | 8 |  | 8 |  | 0 | 12
52 | Desktop | Pre-Order Sales(Parts/Unit Ordering) | 10 |  |  | 10 | 0 | 0
53 | Mobile | Parts/Unit Ordering - LINK TO WEBSITE | 10 |  | 10 |  | 0 | 15
54 | Mobile | Service Scheduling | 10 |  | 10 |  | 0 | 15
55 | Mobile | Cash Count | 15 |  | 15 |  | 0 | 23
56 | Mobile | Approvals | 8 |  | 8 |  | 0 | 12
57 | Mobile | Reimbursement | 10 |  | 10 |  | 0 | 15
58 | Mobile | Random Stock Inventory | 10 |  | 10 |  | 0 | 15
59 | Desktop | Online Credit Application - LINK TO WEBSITE | 10 | 10 |  |  | 15 | 0
60 | Desktop | Online Employment Application - LINK TO WEBSITE | 10 | 10 |  |  | 15 | 0
97 | Desktop | Event schedules and service reminders | 45 |  |  | 45 | 0 | 0
98 | Desktop | Text notification for employee applications(Receipt of application, Rejection) | 3 | 3 |  |  | 5 | 0
99 | Mobile | Health Checklist App | 8 |  | 8 |  | 0 | 12
100 | Desktop | General Services App | 15 | 15 |  |  | 23 | 0
100 | Mobile | General Services App | 40 |  | 40 |  | 0 | 60
Note on C13: Michael Cuison: Include all bills: PLDT/GLOBE/RENTAL. Automatic notification 10 days before due date.

## Desktop
New | Type | Project Name | MIS Est. | Mgmt. Est.
2 | Desktop | Engineering Inventory Management System | 30 | 45
3 | Desktop | Los Pedritos Integrated Systems | 60 | 90
4 | Desktop | 2H MC Pricelist | 15 | 23
5 | Desktop | Online Credit Application | 6 | 6
6 | Desktop | Online Employment Application | 6 | 6
7 | Desktop | Link HCM with Online Application from Website/Android | 5 | 8
10 | Desktop | Incorporate DP Discount on MC Sales for installed Guanzon App | 10 | 15
11 | Desktop | Require OTP on releasing giveaways on MC Sales | 5 | 8
12 | Desktop | Recurring Expenses | 8 | 12
13 | Desktop | Incorporate rebate coupon for every service(Service rebate coupon) | 5 | 8
17 | Desktop | Branch efficiency to be monitored by selling branch not collecting branch | 3 | 5
18 | Desktop | Monitoring of approved applications pending sales | 2 | 3
19 | Desktop | Adjust telemarketing approved credit application retreival to 3 days | 1 | 2
21 | Desktop | Incorporate duration of special promo rebates on encoding MC Sales | 5 | 8
22 | Desktop | Integrated Replication For Multiple Database | 10 | 15
26 | Desktop | MP Consignment Payment | 5 | 8
28 | Desktop | Integrate MC/MP Purchase Order thru General Accounting System | 8 | 12
29 | Desktop | Separate BNOS sales and inventory of 2H shops | 3 | 5
30 | Desktop | Advance Payment/COD Monitoring | 6 | 9
32 | Desktop | 201 File Update | 3 | 5
34 | Desktop | Text notification for Pay Slip of Monarch engineering workers | 3 | 5
35 | Desktop | Payroll Encryption System | 5 | 8
36 | Desktop | Approval Code (S' Jo, S' Guan, S' Arnold) | 6 | 9
37 | Desktop | Random Sending of Pay Slip | 15 | 23
38 | Desktop | FSC & WRC Report | 4 | 6
39 | Desktop | IOM Issuance | 15 | 23
40 | Desktop | Change Unit, Name, Address Monitoring(Reports) | 3 | 5
41 | Desktop | Warranty Claims Report | 4 | 6
42 | Desktop | Midtier Utility Between Cervo and Pedritos Systems | 30 | 45
43 | Desktop | Payroll Reports | 8 | 12
44 | Desktop | Midtier Utility Between Telecom POS and Telecom | 20 | 30
45 | Desktop | Midtier Utility Between IntegSys POS and IntegSys | 20 | 30
46 | Desktop | Management Report (Pedritos Integrated Systems) | 30 | 45
49 | Desktop | Advance Payment thru Gcash | 10 | 10
52 | Desktop | Pre-Order Sales(Parts/Unit Ordering) | 10 | 10
59 | Desktop | Online Credit Application - LINK TO WEBSITE | 10 | 15
60 | Desktop | Online Employment Application - LINK TO WEBSITE | 10 | 15
97 | Desktop | Event schedules and service reminders | 45 | 45
98 | Desktop | Text notification for employee applications(Receipt of application, Rejection) | 3 | 5
100 | Desktop | General Services App | 15 | 23
|  |  | 462 | 663
Note on C10: Michael Cuison: Include all bills: PLDT/GLOBE/RENTAL. Automatic notification 10 days before due date.

## Mobile
New | Type | Project Name | MIS Est. | Mgmt. Est.
1 | Mobile | Collection(DCP) | 20 | 30
8 | Mobile | Integration of Telecom and IntegSys | 15 | 23
9 | Mobile | Credit Investigation | 15 | 23
14 | Mobile | Online Credit App - Applicant photo capture | 10 | 15
15 | Mobile | Selfie Login | 8 | 12
16 | Mobile | Online Credit App - Document scanning | 15 | 23
20 | Mobile | Daily Branch Opening Notification | 8 | 12
23 | Mobile | Attendance summary Notification | 10 | 15
24 | Mobile | Service Hotline | 10 | 15
25 | Mobile | Branch Performance Monitoring | 10 | 15
27 | Mobile | 360 Evaluation | 15 | 23
31 | Mobile | Leave, OB, etc entry for managers/supervisors | 20 | 30
33 | Mobile | Payslip | 10 | 15
47 | Mobile | Notification/Messaging | 15 | 23
48 | Mobile | Notification/Messaging | 10 | 15
50 | Mobile | Advance Payment thru GCash - LINK TO WEBSITE | 10 | 15
51 | Mobile | Pre-term Computaion | 8 | 12
53 | Mobile | Parts/Unit Ordering - LINK TO WEBSITE | 10 | 15
54 | Mobile | Service Scheduling | 10 | 15
55 | Mobile | Cash Count | 15 | 23
56 | Mobile | Approvals | 8 | 12
57 | Mobile | Reimbursement | 10 | 15
58 | Mobile | Random Stock Inventory | 10 | 15
99 | Mobile | Health Checklist App | 8 | 12
100 | Mobile | General Services App | 40 | 60
|  |  | 320 | 483